Parallel Token Swapping on Heavy-Hex Architectures: Approximation Guarantees and an Empirical Router

Undergraduate Thesis Proposal

[Your name]  ·  [Department]  ·  [Date]  ·  Proposed supervisor: [Name]

# 1.  Summary

Quantum circuits must be compiled to hardware with limited qubit connectivity, which requires inserting SWAP gates to bring interacting qubits into adjacency. Because decoherence is a function of wall-clock time, the quantity that matters most is SWAP depth — the number of parallel swap rounds — rather than total SWAP count.

The abstract form of this subproblem is parallel token swapping: given a graph and a target permutation, reach it in the fewest rounds, where each round applies a matching of simultaneous swaps. Constant-factor approximation algorithms are known for cycles, subdivided stars, and grids. They are not known for heavy-hex, the topology IBM ships.

This thesis attacks the heavy-hex case. It proceeds theory-first, but builds the implementation and benchmarking infrastructure early, so that the empirical contribution is secured before the theoretical one is attempted.

# 2.  Problem statement

Parallel token swapping (PTS).  Let G = (V, E) be a graph with a distinct token on each vertex, an initial placement f₀, and a target placement fₜ. A round applies a matching M ⊆ E, swapping the tokens on both endpoints of each edge in M simultaneously. Minimize the number of rounds required to transform f₀ into fₜ.

Heavy-hex.  A hexagonal lattice with additional qubits subdivided onto its edges, giving a mixture of degree-2 and degree-3 vertices. For an i × j grid of hexagons, n = 5ij + 4(i + j) − 1.

Natural lower bound.  LB is the maximum, over all tokens, of the graph distance between that token's starting vertex and its target vertex. The stretch factor of a graph family is the supremum of OPT / LB over all instances in the family.

## Scope caveat

PTS fixes the target permutation. Full qubit routing does not — the router chooses intermediate permutations subject to a sequence of gate constraints, and choosing well is most of the practical problem. An approximation bound for PTS on heavy-hex does not imply a bound on compiled circuit depth. This thesis claims theory at the permutation level and evidence at the circuit level, and will not conflate them.

# 3.  Related work and the gap

Sequential token swapping is NP-hard and APX-hard, with a general 4-approximation and an ETH-based lower bound ruling out 2^o(n) exact algorithms (Miltzow et al., ESA 2016). Trees admit a 2-approximation, independently rediscovered three times, and no better factor is known.

Parallel token swapping was introduced as “routing permutations via matchings” (Alon, Chung & Graham 1994), who bounded any n-vertex tree by fewer than 3n rounds, later improved to (3/2)n + O(log n). It is NP-complete on bipartite maximum-degree-3 graphs — a class containing heavy-hex — and NP-complete even when restricted to three rounds. Bansal, Günlük & Shapley (Discrete Applied Mathematics, 2025; arXiv:2411.18581) give the first constant-factor approximations for cycles, subdivided stars, and grids, and analyze stretch-factor tightness. General graphs remain open, and heavy-hex is not covered.

Heavy-hex routing already has results, but they are different objects. Weidenfeller et al. (arXiv:2202.03459) prove a heavy-hex swap strategy achieving full connectivity in fewer than n + √n + 61 layers — a worst-case diameter bound, not an approximation ratio. Line-graph qubit routing (arXiv:2306.05385) is a deterministic heavy-hex router that beats SABRE on depth by roughly 3.5× for line-graph input circuits — a structure-exploiting heuristic with an overhead bound, not an instance-wise guarantee.

Practical routers. SABRE (Li, Ding & Xie, ASPLOS 2019) is the Qiskit default; TOQM, Duostra, QMAP, and BQSKit target depth more directly. A 2025 benchmarking study found SABRE consistently strongest among general-purpose routers on both count and depth objectives for random circuits, indicating that reported wins over SABRE typically come from exploiting structure rather than from better search.

The gap this thesis targets: no instance-wise approximation guarantee for parallel token swapping on heavy-hex, and no published stretch-factor analysis for the family.

# 4.  Research questions

RQ1.  What is the stretch factor of the geodesic lower bound on heavy-hex graphs?

RQ2.  Does heavy-hex admit a polynomial-time constant-factor approximation for parallel token swapping?

RQ3.  How do the Bansal–Günlük–Shapley algorithms perform empirically against SABRE-class heuristics on benchmark circuits, and where does the worst-case guarantee begin to pay off?

# 5.  Approach

## Phase 1 — Infrastructure (weeks 1–8)

Implement the BGS approximation algorithms for cycles, subdivided stars, and grids. No public implementation is known to exist; producing one is a contribution in itself. Build an exhaustive / ILP solver for optimal PTS on small instances, plus a benchmark harness with matched seeds, matched trial budgets, and depth measured after full transpiler optimization.

This phase is not preparatory overhead. Computational search on small heavy-hex instances is the intended route to the RQ1 conjecture.

## Phase 2 — Stretch factor, RQ1 (weeks 6–15)

Compute OPT / LB exhaustively on small heavy-hex graphs, identify the extremal structures, conjecture a bound, and prove it. This is the primary theoretical target because it is self-contained, empirically attackable, standalone-useful to heuristic designers, and a likely lemma for RQ2.

Concurrently, test whether the known NP-completeness reduction on bipartite degree-3 graphs embeds into heavy-hex. This is cheap and delimits what is provable.

## Phase 3 — Approximation, RQ2 (weeks 15–24)

Primary route (unfolding).  Heavy-hex unfolds along a long induced path covering roughly 4n/5 of its vertices, with pendant vertices attached at every fourth position. Paths admit an additive approximation using only one extra round. Strategy: route along the unfolded line using the known path algorithm, then bound the cost of servicing pendant vertices by O(1) additional rounds per unit. Constant plus constant is a constant factor.

Backup route (composition).  Decompose heavy-hex into cycle and subdivided-star substructures, compose the BGS approximations, and accept a worse multiplicative constant.

## Phase 4 — Evaluation and writing (weeks 22–30)

Benchmark on QASMBench and MQT Bench against SABRE (optimization_level = 3, matched trials), Duostra, QMAP, and tket. Report the depth / count Pareto frontier, not a single metric — depth reductions bought with large SWAP-count increases can be net fidelity losses.

# 6.  Decision gate

At week 16, the following must hold to continue Phase 3: either a proven stretch-factor bound for at least one heavy-hex family, or a complete proof sketch of the pendant-servicing lemma.

If neither holds, Phase 3 is abandoned and effort redirects to extending Phase 4 into a full comparative study, including negative results on why the subdivided-star technique fails to generalize. The gate is a fixed calendar date with binary criteria, not a judgment call.

# 7.  Deliverables

- Open-source implementation of the BGS algorithms (Python; Rust / PyO3 only if time permits), exposed as a Qiskit TransformationPass.

- Exhaustive PTS solver and benchmark harness with reproducible configuration.

- Stretch-factor analysis for heavy-hex, with proof if attained.

- Approximation algorithm with proof, if attained.

- Comparative benchmark study on QASMBench / MQT Bench with Pareto analysis.

- Thesis document.

# 8.  Success criteria

| Level | Criterion |
| --- | --- |
| Threshold | Working implementation of published algorithms; rigorous comparative benchmark study; documented negative results. Achievable regardless of theoretical outcome. |
| Target | Proven stretch-factor bound for heavy-hex, validated computationally. |
| Stretch | Constant-factor approximation for parallel token swapping on heavy-hex. |

The threshold level is reachable by construction, since it depends only on implementing existing results and running experiments. This is deliberate.

# 9.  Risks

| Risk | Mitigation |
| --- | --- |
| Proof does not close | Week-16 gate with binary criteria; threshold deliverable already secured by then. |
| Scooped — heavy-hex is the obvious next increment after subdivided stars | Monitor arXiv and citations to BGS weekly; a concurrent result still leaves the empirical study intact. |
| Benchmarking methodology criticized | Matched seeds and trial budgets from the start; report Pareto frontiers; publish full configuration. |
| Implementation scope creep | Python first; Rust is explicitly optional. |
| Supervision mismatch on combinatorics | Raised explicitly in Section 10. |

# 10.  Questions for my supervisor

- Can you supervise a combinatorial optimization proof, or should I seek a co-advisor from theory / discrete mathematics?

- Does the department expect novelty in an undergraduate thesis, or is demonstrated research competence sufficient? This determines how much weight the theory arm should carry.

- Is the week-16 gate structure acceptable as a formal checkpoint?

- What compute is available for exhaustive small-instance search and benchmark sweeps?

# 11.  Key references

- Bansal, Günlük & Shapley. Parallel token swapping for qubit routing. Discrete Applied Mathematics (2025). arXiv:2411.18581

- Miltzow, Narins, Okamoto, Rote, Thomas & Uno. Approximation and hardness of token swapping. ESA (2016)

- Alon, Chung & Graham. Routing permutations on graphs via matchings. SIAM J. Discrete Math (1994)

- Aichholzer et al. Hardness of token swapping on trees. arXiv:2103.06707

- Weidenfeller et al. Scaling of QAOA on superconducting qubit based hardware. Quantum 6, 870 (2022). arXiv:2202.03459

- Line-graph qubit routing: from kagome to heavy-hex and more. arXiv:2306.05385

- Li, Ding & Xie. Tackling the qubit mapping problem for NISQ-era quantum devices. ASPLOS (2019)

- Quetschlich, Burgholzer & Wille. MQT Bench. Quantum 7, 1062 (2023)